## Slide 1
Developed by the GEMNet-Health Task Group on Curriculum for Postgraduate Evaluation Courses
MODULE 6:
Evaluating Results
Evaluation of Health Programs A Postgraduate Overview Course

## Slide 2: Module 6
At the end of the module, students will be able to:
Identify data sources to analyze program performance and track program outcomes
Illustrate the use of qualitative and quantitative data to assess program performance
Track program results and compare actual performance versus goals
Sessions:
Session 1: Developing Performance Monitoring Plans/M&E Plans (3 hours)
Session 2a: Tracking Results/Changes (3 hours)
Session 2b: Appraising Results (4 hours)
Learning objectives and sessions
Notes: This module covers evaluating results. At the end of the module, students will be able to:
  Identify data sources to analyze program performance and track program outcomes
  Illustrate the use of qualitative and quantitative data to assess program performance
  Track program results and compare actual performance versus goals
This module is divided into two sessions. The second session is also divided up into two sub-sessions.
  Tracking results/changes
  Appraising results

## Slide 3
Module 6, Session 2A
Tracking results/changes

## Slide 4
Objective
  Understand the process of implementing an M&E plan
  Identify some challenges with implementing an M&E plan
Outline
  Definition: What is meant by tracking program results
  Importance of tracking program results
  Key steps in tracking program results
  Selecting and evaluating key performance indicators to monitor outcomes
  Developing a data collection plan
  Data analysis
  Dissemination plan
  Cost of implementing M&E plan
  Challenges with tracking program results
Objective and Outline
Session 2A: Tracking results/changes
Notes: Speaker notes:
  Session 1 introduced us to the development and components of an M&E plan
  In this session, we will be covering, in more detail, implementing an M&E Plan or tracking program results. Specifically:
    Definition: What is meant by tracking program results
    Importance of tracking program results
    Key steps in tracking program results
    Selecting and evaluating key performance indicators to monitor outcomes
    Developing a data collection plan
    Data analysis
    Dissemination plan
    Cost of implementing M&E plan
    Challenges with tracking program results

## Slide 5
Definition:
Tracking program results
M&E plan is a document that helps to track and assess the results of the interventions throughout the life of a program/policy/intervention
Tracking is a continual process (measuring, learning, improving) which involves data collection and measurement of program indicators to evaluate project/program target
In monitoring, tracking results will mean:
  To track and assess performance through analysis and comparison of indicators over time
In evaluation, tracking results will mean:
  To evaluate achievements or outcomes by comparing indicators before and after an intervention
Notes: Speaker notes:
  Tracking results involves implementation of the M&E plan, which was discussed in detail in Session 1
  Emphasise that tracking results is not a static process—it continues with the project until the end, and sometimes even a few months afterwards

## Slide 6
Importance of Tracking Program results
Evaluate program performance and success
Identify specific areas for improvement or expansion
Monitor trends against overall target
Make well informed decisions about future policies, goals, and actions
Notes: Speaker notes:
  Ask participants to discuss the importance of program tracking
  All participants should be allowed to make a contribution

## Slide 7: Key Steps for Tracking Program results
Identify key performance indicators
Setting the baseline year
Clearly define targets
Develop a plan to track results
Collect comprehensive data on the key indicators
Analyze data and evaluate short, medium, and long term impacts
Plan for dissemination
Notes: Speaker notes:
  Emphasise this point as most important: The aim is to guide students to understand how to track program results
  Note that the development of a plan here is different from the M&E plan; this is more of a plan on your goals and how you intend to track your results, including using data sources, identifying relevant indicators, and analysing data analysis among other things
    While some of the steps overlap with developing an M&E plan, they are action-based steps that should complement and draw from the M&E plan

## Slide 8: Step 1: Identifying Key Performance indicators – I
An indicator is a variable that measures an aspect of a program or health outcome
  Characteristically, they can be measured as counts, percentages, ratios, rates, index, thresholds, etc.
Types of indicators
  Process indicators
  Outcome indicators
Notes: Speaker notes:
In Session 1, you were introduced to “performance indicators” as a key component of an M&E plan. Here, we will go into more detail about selecting indicators, operationalizing indicators, linking indicators to frameworks, and setting targets, and have the opportunity to participate in class activities relating to indicators as well.
Step 1: identifying key performance indicators
  Indicator metrics
    Counts
      Number of providers trained
      Number of condoms distributed
    Calculations: percentages, rates, ratios
      % of facilities with trained provider
      Maternal mortality ratio; total fertility rate
    Index, composite measures
      Quality index comprising the sum of scores on six quality outcome indicators
      Disability adjusted life years (DALY)
    Thresholds
      Presence; absence
      Predetermined level or standard
  Engage students in discussion on their understanding of process and outcome indicators

## Slide 9
Important steps
  Step 1A: Characteristics of good performance indicators include being:
    Measurable
    Accessible
    Relevant, in reference to the project objectives
  Step 1B: Overview of the logic model (input, output and outcomes: Short term, medium, and long term)
  Note: The indicator should be able to provide enough relevant information to evaluate/ assess project goals and objectives
Step 1: Identifying Key Performance indicators – II
Notes: Speaker notes:
Team should brainstorm based on the characteristics of a good performance indicator, such as being:
  Measurable
  Accessible
  Relevant in reference to the project objectives

## Slide 10
Valid: accurate measure of a behavior, practice, or task
Reliable: consistently measurable in the same way by different observers
Precise: operationally defined in clear terms
Measurable: quantifiable using available tools and methods
Timely: provides a measurement at time intervals relevant and appropriate in terms of program goals and activities
Programmatically important: linked to a public health impact or to achieving the objectives that are needed for impact
Characteristics of Good Indicators

## Slide 11
  Class discussion:
  Is parasitemia a valid measure of morbidity?
  Is fever a valid measure for malaria?
  Is parasite testing a valid measure for parasite prevalence?
  Is the number of people reached by behavior change communication (BCC) campaigns a valid measure of malaria knowledge?
Validity: Class Activity 1
Notes: Answer key:
  No, you could test positive for malaria parasites and have no symptoms in stable transmission areas
  No, fever can be caused by other diseases (e.g., pneumonia)
  Yes, because it measures what it says it measures
  No, they could be reached and have no knowledge

## Slide 12: Measurable: Class Activity 2
Class discussion:
How would you measure this (what method, source, tool, etc.)?
  Number of ITNs distributed
  Compliance to antimalarial treatment
  Anemia
  Parasitemia
Notes: Answer key:
  Yes
  No, unless observed
  Yes
  Yes

## Slide 13: Programmatically Important: Class activity 3
Class discussion:
Are the following indicators programmatically important (i.e., linked to a public health impact or to achieving the objectives needed for impact)?
Example 1: Insecticide-treated mosquito nets (ITN) distribution program
  Indicator: # of ITNs distributed in the past quarter
Example 2: Program to increase access to ACTs through community-based health workers
  Indicator: Number of ACT sales points with antimalarial drugs
Notes: Yes
No, it should be the number of CBWs providing ACTs

## Slide 14: Operationalizing Indicators
Establish exactly how a given concept/ behavior will be measured
  Precise definition and metric
  How the value will be reliably calculated
  Anyone using the same data will arrive at exactly the same indicator value
  Challenges
    Subjective judgment
    Local conditions
    Unclear yardsticks
    Skills of the users

## Slide 15
How Indicators Are Linked to Frameworks
Notes: Speaker notes:
This example demonstrates how indicators are related to logic models. Ask participants to think of an indicator for output, outcome, and impact before showing them.

## Slide 16: Results frameworks use indicators
How Indicators Are Linked to Frameworks
Notes: Ask participants to think of an indicator for each IR before showing them.

## Slide 17
Choose a particular year that would be logical for the baseline year
Remember: You will compare the performance of the project to the baseline year
  What do we need before we choose a particular year as the baseline line year?
  Key: Are data measuring key performance indicators available for that year?
Step 2: Setting the Baseline Year
Notes: Speaker notes:
  If it is a new intervention you are introducing, then the baseline will be the time just before the intervention; here all indicators relevant for the projection would have been identified and should be measured at the baseline before the intervention
  If the program or project already exists, then you will need to settle on an appropriate baseline

## Slide 18: Step 3: Defining Target
Program target can be three-fold:
  Short-term
  Mid-term
  Long-term
Let’s brainstorm about what goes into short-, medium-, and long-term targets
Let’s give examples of outcome indicators and targets for each indicator
Notes: Speaker notes:
  Let’s brainstorm about what goes into short-, medium-, and long-term targets
  Let’s give examples of outcome indicators and targets

## Slide 19
Data Collection, Analysis, and interpretation

## Slide 20
Based on the project goals develop a consistent, efficient, and reliable process for data collection and management
Identify persons responsible for collecting data for each performance indicator, managing the dataset, creating and submitting reports
Identify protocols, templates, sources, units to be used in collecting data
Provide timelines for data collection, analysis, and reporting
Brainstorm on how to ensure data integrity and security
Allocate sufficient resources (money, time, staff, etc.) for each activity associated with tracking and reporting
Minimize the burden of data requests by integrating with existing processes and procedures
Move to baseline data collection
Start by collecting data for the baseline year
Commence regular data collection based on the tracking plan
Step 4: Developing a Plan for data collection
Notes: Speaker notes:
The next section of the plan describes from where the information for the indicators will come. This section would include the various sources of information and diagrams of how that information is reported and how the M&E unit would obtain that information. There will be a more detailed session on M&E information sources later.

## Slide 21: Step 5: Collect Comprehensive Data on key indicators
Sources of data for indicators
Diagram of data collection, processing, analysis, and reporting system
Data collection tools
  Patient records or registers
  Survey instruments
  Commodity management forms (e.g., condoms)
  Others?
Management
  Roles and responsibilities of each group/member of the system
Data quality
Notes: Speaker notes:
An analysis of the strength of the information system would be important to assess the validity of the information that is obtained.
For data collected by the program’s M&E unit, there should be more detail given than for data collected by organizations external to the M&E program.

## Slide 22: Data Quality Constraints
Describe known constraints to data quality and/or system performance and what will be done to address these
Name of indicator | Data quality issues | Actions taken or planned to address this limitation | Additional comments
(list by indicator) | List possible risks to the quality of data collected. Consider the five criteria for data quality: validity, reliability, integrity, precision, and timeliness. | How will the identified possible risks to the quality of data be managed? | 
Notes: Criteria of data quality
Validity
  Characteristic of a measurement tool measures what the researcher actually wants to measure
  Have we actually measured what we intended?
Reliability
  “A characteristic of measurement concerned with consistency”
  Can we consistently measure what we intended?
Timeliness
  The relationship between the time of collection, collation, and reporting to the relevance of the data for decision-making processes
  Does the data still have relevance and value when reported?
Precision
  Accuracy (measure of bias)
  Precision (measure of error)
  Is the margin of error in the data less than the expected change the project was designed to effect?
Integrity
  Measure of “truthfulness” of the data
  Is the data free from “untruth” introduced by either human or technical means, willfully or unconsciously?

## Slide 23: Step 6: Data Analysis and evaluation
Evaluation is the process of analyzing changes in your indicators to determine which elements of your program are effective and which aspect of the project needs to be modified to achieve project objectives
  Process evaluation: assess if the program is being implemented as planned or according to protocol
  Impact evaluation: assess whether or not the program is having the desired impact or effect and that the observed change can be attributed to the implementation of the project
Notes: Speaker notes:
Analyse short-, medium-, and long-term impacts of a project/program.

## Slide 24
Relevant questions:
  How much progress has been made between the baseline data and the post-implementation data?
  Are the results on track for achieving interim and long-term targets?
  What other factors or programs could have influenced the change between the baseline and post-implementation year?
  Do the data support our narrative?
  Document evaluation process and assumptions
Step 6: Data Analysis and evaluation

## Slide 25: Methods for Data Collection and analysis
Quantitative design: Structured questionnaire to measure performance indicators, review of records (secondary data)
Qualitative design: Focus group discussion, in-depth interview
Analysis: Frequency, percent frequency, rate, counts, t-test for comparing difference in means, Z-test for comparing difference in proportion, and quasi-experimental design procedures

## Slide 26: Confounders
A confounder is a variable that has an effect on a program, outcome variable of interest, or both
Essential to control for confounders to be able to quantify the effect of the program on the outcome of interest
Ways of controlling for confounders:
Stratified analysis—Mantel Haenzel procedure
The use of regression models
Notes: Now, we will touch on a some challenges with respect to evaluating results, such as confounding, bias, selection, and statistical power.

## Slide 27
Selection bias arises when subjects are selected to receive the program based on characteristics that may also affect their outcomes.
Any observed difference in outcomes between program and comparison groups can be attributed to both the program impact and pre-existing differences between the groups.
Non-participants are often a poor comparison group for participants
Participants are not a random sample of the target population
Participants selected through program placement rules and self-selection
Participants may differ systematically from non-participants
Selection Bias

## Slide 28: Randomization Solves Selection Bias
Selection bias occurs because of systematic differences between participants and non-participants:
  If program and comparison groups are drawn at random from the same underlying population, then the characteristics of the two groups will be identical on average
  The program and comparison groups are identical except that one got the intervention and the other did not
  The outcomes of the two groups would have been the same if neither received the intervention—implies selection bias = 0
  Any differences observed in outcomes between the two groups must be attributable to the intervention

## Slide 29: Power of a Statistical Test
The statistical power is the ability of a statistical test to detect a difference of a specified magnitude given that this difference exists in the populations being compared
Unlike , power is not the risk of a particular error; instead, it is the probability that a statistical test will reach a particular correct conclusion

## Slide 30: Factors That Influence the Power of a Study
Sample size: Increasing sample size increases power
The variability of the observation: Power increases as variability of the observation decreases
The effect size: Power increases as the effect size of interest increases
Significance level: The power is greater if the significance level is larger. That is, type I error increases as the type II error (decreases

## Slide 31
Treatment on the treated estimate (TOT)
Remember: The ITT and TOT estimates will be the same when there is full compliance; that is, when all units to whom a program has been offered actually decide to enroll in it
Discuss results based on program objectives
Interpretation and Discussion of Results
Notes: Treatment on the treated estimate (TOT): This is when the basic impact evaluation formula is applied to those units to whom the program has been offered and who have actually enrolled.
Remember: The ITT and TOT estimates will be the same when there is full compliance; that is, when all units to whom a program has been offered actually decide to enroll in it.
Discuss results based on program objectives:
Were the objectives achieved? If not, what could be possible explanations for why the target was not achieved?
If the target was achieved, what could account for that for sustainability?

## Slide 32
Qualitative Designs
for data collection and analysis

## Slide 33
Phenomenology
  Purpose: to describe experiences as they are lived
Grounded theory
  Purpose: theory development
Ethnography
  Purpose: to describe a culture's characteristics and its impact on the behaviour/outcome we are interested in
Study Designs
Notes: Study designs in qualitative research include:
Phenomenology
  Purpose: to describe experiences as they are lived
Grounded theory
  Purpose: theory development
Ethnography
  Purpose-to describe a culture's characteristics and its impact on the behaviour/outcome we are interested in

## Slide 34
Narratives
  Purpose: describe and examine events of the past to understand the present and anticipate potential future effects
Case study
  Purpose: describe, in-depth, the experience of one person, family, group, community, or institution
Study Designs

## Slide 35
Qualitative sampling is generally “purposive”
  Respondents, settings, or events with particular characteristics that relate to the research question are selected to take part
“Theoretical sampling” is a specific, theory-driven form of purposive sampling
  A small number of respondents selected and interviewed, a hypothesis is developed, and further respondents are selected who might challenge the hypothesis
  – Glaser and Strauss, 1967
Sampling

## Slide 36
Stratified purposive sampling
Snowballing
Maximum variation
Key informants/experts
Consecutive
Convenience
Sampling
Notes: Stratified purposive sampling (stratify accordingly to known groups)
Snowballing (e.g., select initial respondents, then initial respondents help to recruit more)
Maximum variation (as wide a range as possible; e.g., old, young, men, women)
Key informants/experts (selection of especially knowledgeable or relevant people)
Consecutive (e.g., consecutive patients)
Convenience (e.g., people who are available)

## Slide 37
  Interviews (in-depth/ semistructured)
  Focus groups
  Participant observation
  Observation
  Documentary analysis
Data Collection Approaches

## Slide 38
Field notes
Interviewer’s notes
Interview guide
Audio tape/digital voice recordings, transcripts
Topic guide
Document and artifacts
Visual media
Data Collection Tools
Notes: Whatever be your chosen methods of data collection—please pilot and review the data from the pilot to ensure that you have chosen the most appropriate data collection methods for your evaluation.
Participatory rapid appraisal, rapid anthropological procedures, rapid ethnographic assessment
Body mapping: Social maps of resources, maps of barriers
Pile sorting: Cards which list out common sources of malaria and participants asked to choose/list in order of importance what is there

## Slide 39: Steps in the Data Management Process
Make copies of all materials
Put field notes in some order
Management system for all interviews, surveys, and questionnaires
Create a catalog of all materials relevant to the research
Check for missing data
Notes:   Making copies
  Hard copy vs. soft copy
  Store copies in different formats, and in different locations
  Various ways available to maintain field notes
    Chronological
    Genre files
    Topical files
  Management system
  Label each recording/note(s)
  Use an identification number for each interview/FGD transcript
  Helps to monitor progress and easy retrieval
  Cataloging
  Helps in quick retrieval
  Keep the catalog separate from the original data
  Missing data
  Easier to obtain data when you are still in the field or immediately after you have left it

## Slide 40: Data Collection and Analysis
Data analysis informs further data collection
Data collected
Data processed
Data analysed

## Slide 41
Identifying patterns, underlying themes, commonalities, and differences
  Thematic analysis
  Content analysis
Qualitative data analysis can be done manually or with software, such as:
  AtlasTi
  MAXQDA
  QSR NVivo
  EZ-TEXT 3.06C
Analysis Plan for Qualitative Data

## Slide 42
Ethnography (Anthropology)
Immersion in a context; holistic; reflexive
Grounded theory (Glaser and Strauss)
  Constant comparison
  Cyclical process of research
  Theory-driven
  Induction
Framework method (Ritchie and Spencer)
  Coding into a thematic framework
  Applied research
Interpreting Data
Notes: Strategies for interpretation
Ethnography: Mainly stems from anthropology—immerses researcher in a setting and the researcher examines social structure (local social organization, hierarchies, subgroupings; i.e., arrangements of power) and culture (practices and meanings). This approach examines as much as possible—so that the research includes context and environment as well as individuals.
Ethnography is also highly reflexive—it acknowledges, and to a certain extent embraces, the presence and role of the researcher.
Information gathering and interpretation are thereby intertwined.
Second, Glaser and Strauss developed a strategy, called grounded theory, for dealing systematically with data.
In this, information is interpreted through coding, comparison, and a constant process of to-ing and fro-ing within the data set
  The idea is to develop theoretical notions from the material itself; there is a drive to develop theory in a process of moving from the particular to the general—induction
Similar to grounded theory you may come across the “framework method,” which was developed by the National Centre for Social Research especially for interview and focus group material. It is a content analysis method which involves summarising and classifying data within a matrix (“charting”) and hence a thematic framework. It is favoured for policy analysis.

## Slide 43
Internal validity: credibility
External validity: transferability
Validity in Qualitative Research

## Slide 44
How believable are the research findings?
How to improve credibility:
  Good design appropriate to the question
  Triangulation
  Robust analysis (e.g., double coding)
  Checking with the participants
  Attention to negative cases
  Good description of methods in write-up
Credibility

## Slide 45
Would your research findings apply in other settings?
Transferability might not mean “better” research
Transferability

## Slide 46
Quantitative Designs
for data collection and analysis

## Slide 47
We will identify various evaluation designs:
  Experimental
  Quasi-experimental
  Non-experimental
Evaluation Designs
Notes: Speaker notes:
Evaluation designs will be not be addressed in detail in this session. Rather, they will be covered in other modules.
In this session, we will just touch on evaluation design by examining appropriate and inappropriate criteria for inferring causality and identifying various group designs, including: experimental, quasi-experimental, and non-experimental, and the ways in which they attempt to show causality.

## Slide 48: Types of Evaluation Designs
Design | 
Experimental | Strongest for demonstrating causality, most expensive
Quasi-experimental | Weaker for demonstrating causality, less expensive
Non-experimental | Weakest for demonstrating causality, least expensive
Notes: 48
Speaker Notes
There are three types of evaluation designs – 1) one (experimental) is very close to a laboratory environment, 2) non-experimental, the one furthest removed from an ideal laboratory environment and 3) one which is in the middle between the two in terms of idealness. The three differ in the sort of conclusions you can draw and some are more expensive than others.
Speaker notes:
There are three main evaluation design categories. We will cover each of these in more detail.
Experimental design is the strongest design for demonstrating causality, but it is also the most expensive.
Quasi-experimental design is not as good for demonstrating causality, but is less expensive than experimental design.
Non-experimental design is the weakest for demonstrating causality and is also the least expensive evaluation design.

## Slide 49
Measuring the effect of an intervention
Notes: Speaker notes:
This is a diagram which simply demonstrates the effect of a program over time. The lower line shows that without the program, the effect we are looking at has a certain natural trend. It could be upward or downward or some other trend. For instance, deaths could have been declining well before your program as a result of overall improvements in housing and nutrition in a population. The upper curve shows what happens when you intervene; for instance, you introduce a better curriculum in a school, as well as better teachers, and there is an increase in the overall math scores. The evaluator would then compare the trend before the intervention to that after the intervention. The difference—the red part of the diagram—is the program or intervention effect.
49

## Slide 50: Step 7: Plan for Dissemination and use
Clearly defined users
Databases for information storage
Dissemination methods
  Reports (schedule and audience)
  Media
  Speaking events
  Others?
Notes: The next section of the plan will describe how the information that the M&E plan describes will be disseminated and used.
This ensures that findings from M&E efforts are not wasted because they were not shared. Desired information should be defined at the beginning of the M&E planning stage so that results and feedback are planned accordingly. This portion of the plan highlights that skills in communicating to a variety of audiences, including policymakers and program officials, are critical.
A database may be used to store indicator information or catalogue research findings and other resources.
Users of the various types of information should be clearly defined and the reports that will be produced described.
Sometimes, information utilization models will be used and these should be listed. This would create a picture of how information is kept, disseminated, and utilized by policymakers and others.

## Slide 51: Reporting and Modifying project content
Use the findings from your evaluation to inform stakeholders and improve program performance
Know your audiences, their informational needs, and the best ways and times to reach them
Identify program strengths, weaknesses, and opportunities
Modify program activities and continue to track results to see the impact of the adjustments
Consider how program results can be used to inform budget and strategic planning processes
Continue the process of collecting and evaluating data, reporting progress, and making program refinements for (at least) the duration of your program
Notes: Source: This was adapted from the United States Environmental Protection Agency’s (US EPA) State and Local Climate and Energy Program November 18, 2014.

## Slide 52
Using the case study, develop a data collection matrix to evaluation control and management of JE outbreak.
Consider the following issues:
Who will be responsible for data collection and its supervision?
Who will be responsible for ensuring data quality at each stage?
How will data quality be checked at every stage?
How often will the data be collected, compiled, sent, and analyzed?
What indicators will be derived from each data source?
How will the data be sent (raw; summary)?
What tools/forms will be used, if any?
What resources (staff, office supplies, computers, transportation) will be needed at each stage?
Who will analyze the data? How often will analysis occur?
How often will the results be compiled into reports?
To whom, and how often, will the results be disseminated?
Class Activity 4: Data Collection Plan
Notes: Refer to the case study on control and management of the JE outbreak.
Class activity 4:
Gather into your groups and develop a data collection matrix for your project. Please consider the issues listed above. You have 30 minutes for this group exercise. Then, each group will have 7 minutes to share their results with the rest of the class.

## Slide 53
Implementing an M&E plan

## Slide 54: Implementing an M&E Plan
Assessment of capacity to implement plan
A detailed work plan of each M&E activity
    Timing of each activity
    Party responsible for each activity
    Budget necessary for each activity
Mechanism for reviewing and updating plan
Costs
Notes: Speaker notes:
The previous sections outlined what the M&E unit will do and the information that will be collected, stored, and disseminated. The next section of the M&E plan details what capacity is needed to implement those functions and how this will be addressed.

## Slide 55: Implementing an M&E Plan: Costs
How much will it cost? Need to budget:
Costs of information systems (costs of data collection, processing, and analyzing)
Costs of information dissemination and use
Costs of the data quality control system
Costs of coordination and capacity building
Notes: Speaker notes:
The costs of the various components of an M&E system will also determine its complexity. Costs that should be considered are those related to the cost of data collection and information dissemination and use and those for M&E coordination.
The next slide will provide an idea about the relative costs of different information systems. The costs of information dissemination and use include those of publishing reports and holding dissemination meetings. The costs of the program’s M&E unit for the coordination of information collection and facility of information use are primarily related to the cost of the human resources and the infrastructure and technology to support them.

## Slide 56: Sample Costs for Selected Data Sources
Information system | Total annual costs (2001 $USD) | Frequency of data collection
National sentinel system | $513,682 | Continuous
HMIS | $2,119,941 | Continuous
Integrated disease surveillance | $4,270,943 | Continuous
Vital registration | $719,427 | Continuous
DHS | $854,164 | Periodic (~4 years)
National census | $8,244,114 | Periodic (~10 years)
Source: Rommelmann, et. al. (2003). Costs and Results of Information Systems for Poverty Monitoring, Health Sector Reform, and Local Government Reform In Tanzania.
Notes: Speaker notes:
This example is for a more general system, but many of the components add to the overall HIV/AIDS M&E system at the national level. For example, the DHS measures behavior change, disease surveillance, and opportunistic infections such as TB.
There are not many studies about the relative costs of different information systems. One study in Tanzania looked at the costs of information systems that collected health-related indicators. The results are presented here.
The authors of this document remind us that the estimates should be compared with caution because of the differing abilities of the organizations to account for their costs. For example, while all the estimates are supposed to be based on costs, the estimates for integrated disease surveillance are based on budgets.
These systems not only differ in the frequency of data collection, but they differ in the number of people that data is collected from. In Tanzania, the National Sentinel System is a system that looks at the health issues of four distinct geographically-based populations. The HMIS covers the entire nation geographically, but only for people who attend health facilities. The IDS and vital registration systems are supposed to cover the entire population of the nation.
The DHS and household budget survey only survey a nationally-representative sample of households. The national census covers the entire population.
Group discussion
Any comments or reactions?
  Cost of a national survey are just under $1,000,000
  The more people that data are collected on (national census, and IDS and HMIS) the more the cost; vital registration disobeys this rule—perhaps a reflection of the weakness of the vital registration?
  If the price of an HMIS is as high as they report, why would you want to use this type of information system?
  If it is comprehensive, complete, and rigorous, it will give an accurate picture of health service utilization
    Health service utilization information is difficult to get from a household survey
  We don’t know if these HMIS costs include setting up the system, overhauling it, or upgrading it—that type of work would be more costly than maintaining the system

## Slide 57: Implementing the M&E Plan: The role of the M&E unit
Consensus building—among all stakeholders
Coordination
Data management, data analysis, and interpretation
Reporting
Information dissemination
Training and capacity building
Notes: Speaker notes:
We’ve talked about an M&E unit. On this slide, we present some of the possible tasks of an M&E unit.
The unit itself may be responsible for actually development (i.e., writing the M&E plan), but in order to do so it may require the building of consensus among stakeholders and coordinating multiple activities.
What is meant by coordination?
Coordinating between various program components (e.g., meeting with staff from different program areas, even within the same program; for example, within HIV/AIDS, meeting with staff from VCT, PMTCT, ARV, CS, etc., to review the indicators that will be used to monitor and evaluate their programs)
Coordinating between other stakeholders to avoid duplication of data collection efforts
Coordinating some data collection efforts (e.g., special surveys/studies)
Data manipulation might include actual data entry and analysis.
Reporting would include actual writing of a regular M&E report or updating on indicators.
The M&E unit might be responsible for disseminating an annual M&E report to all stakeholders and coordinating a review of results to assess program performance and make adjustments.
What are some of the roles/tasks you see as the responsibility of this unit?

## Slide 58: Challenges with Tracking program results
Lack of baseline data to be compared to mid- and long-term data collection for program evaluation
The use of indicators that are not easily measurable
Poor data quality, especially on the over-reliance of secondary data
Needs a lot of time and commitment
Differences in indicators used at baseline and end-line
Missing information on key performance indicators

## Slide 59
Need for plan not well perceived by stakeholders
Costly
Lack of expertise
Time consuming
Challenges in Implementing an M&E plan
Notes: Speaker notes:
Sometimes need is not seen because “strategies may have been proven to work”
Costly—stakeholders may find it a wastage of money
Lack of expertise—the program implementing team may not have the technical capacity to perform M&E activities
Time consuming—properly designing and implementing an M&E plan can take substantial amounts of time that may not be appreciated/valued by stakeholders
Sometimes requires rigorous experimental design, which makes M&E activities unaffordable and unattainable for small-scale programs

## Slide 60
Objective
  Understand the process of implementing an M&E plan
  Identify some challenges with implementing an M&E plan
Outline
  Definition: What is meant by tracking program results
  Importance of tracking program results
  Key steps in tracking program results
  Selecting and evaluating key performance indicators to monitor outcomes
  Developing a data collection plan
  Data analysis
  Dissemination plan
  Cost of implementing M&E plan
  Challenges with tracking program results
Objective and Outline
Session 2A: Tracking results/changes
Notes: Speaker notes:
Session 1 introduced us to the development and components of an M&E plan
In this session, we covered implementing an M&E plan and tracking program results. Specifically:
  Definition: What is meant by tracking program results
  Importance of tracking program results
  Key steps in tracking program results
  Selecting and evaluating key performance indicators to monitor outcomes
  Developing a data collection plan
  Data analysis
  Dissemination plan
  Cost of implementing a M&E plan
  Challenges with tracking program results

## Slide 61: References
Developing Process Evaluation Questions. Evaluation briefs No. 4, CDC. February 2009, www.cdc.gov/healthyyouth/evaluation/pdf/brief4.pdf
http://www.fhi360.org/sites/default/files/media/documents/Monitoring%20HIV-AIDS%20Programs%20%28Facilitator%29%20-%20Module%203.pdf
https://www.oecd.org/dac/peer-reviews/World%20bank%202004%2010_Steps_to_a_Results_Based_ME_System.pdf
Impact Evaluation in Practice, The World Bank. 2011, http://www.worldbank.org/pdt
Introduction to Impact Evaluation. Patricia Rogers. RMIT University. InterAction, https://www.interaction.org/impact-evaluation-notes
Kusek, J.Z., & Rist, R.C. (2004). Ten-steps to a results-based monitoring and evaluation system. A handbook for development practitioners. Washington, DC, USA: The World Bank.
World Health Organization. (2009). Monitoring and Evaluation of Health Systems Strengthening. An operational framework. Geneva, Switzerland: WHO.
Outline of Principles of Impact Evaluation. Part 1 Key Concepts.
Quantitative and Qualitative Evaluation methods. Center for Civic Partnerships. 2014, http://www.civicpartnerships.org/#!quantitative--qualitative-eval-methods/c1bel
Workshop materials from-GEMNet-Health Regional Workshop on Impact Evaluation of Population, Health and Nutrition Programs, https://www.measureevaluation.org/ resources/training/capacity-building-resources/workshop-on-impact-evaluation-of-population-health-and-nutrition-programs/workshop-on-impact-evaluation-of-population-health-and-nutrition-programs-landing-page

## Slide 62
This presentation was produced with the support of the United States Agency for International Development (USAID) under the terms of MEASURE Evaluation cooperative agreement AID-OAA-L-14-00004. MEASURE Evaluation is implemented by the Carolina Population Center, University of North Carolina at Chapel Hill in partnership with ICF International; John Snow, Inc.; Management Sciences for Health; Palladium; and Tulane University. Views expressed are not necessarily those of USAID or the United States government.
www.measureevaluation.org