## Slide 1: Monitoring and Evaluation Frameworks
What is a M&E Framework?
Why do we use M&E Frameworks?
How do we develop M&E Frameworks?

## Slide 2: M&E Frameworks
Models, pictures or maps
Visualize the factors that drive an intervention
Maps that illustrate how a program should work
Identify relationships between factors that influence program operation and the successful achievement of objectives

## Slide 3: Why do we use M&E frameworks?
Communication and planning tool
As a ‘map’ for program’s goals
Links between resources and activities
Guide selection of indicators
Notes: The purposes of designing monitoring and evaluation frameworks include:
  clarifying assumptions, goals, and interrelationships among all kinds of factors relevant to the project or program
  defining levels of performance and desired results in terms of planned activities and realistic, objective impacts
Monitoring and evaluation frameworks incorporate:
  program managers’ assumptions and objectives, in a given context
  a schematic design displaying the directional linkages between key program elements and/or planned results, and other relevant factors

## Slide 4: M&E LOGICAL FRAMEWORKS
Logical Framework:
Logical frameworks are diagrams that identify and illustrate the relationships between program Inputs, Processes, Outputs, and Outcomes.
Purposes:
Provides a linear interpretation of planned use of resources and desired ends
Clarifies project/program assumptions about linear relationships between key factors relevant to desired ends
Notes: <number>
<footer>
<header>
<date/time>
Inputs are necessary to create processes, which drive the production of outputs and outcomes.

## Slide 5
INPUT
Resources
Clinical and managerial Staff
Drugs
Laboratories
PROCESS
NTP – mgt /communication
Communication
Advocacy
Training of staff
Surveillance system
OUTPUT
Diagnostic services
Treatment services
Knowledge
Reduced Stigma
OUTCOME
Case detection
Case treatment
Case holding
IMPACT
TB infection
TB morbidity
TB mortality
CONTEXT
Political commitment Health system Socio-economic conditions Epi-context
Availability HIV prevalence
Access Malnutrition
Utilization Alcoholism
M&E logical framework for TB programme
Notes: Here is a generic example of an M&E framework for a national TB program. This framework shows the linear relationships between inputs, processes, outputs, outcomes, and impact. It also provides a visual interpretation of the broad context for the NTP, which includes: Political commitment
Health system variables
Socio-economic conditions
Epidemiological context of TB

## Slide 6
INPUT
Drugs
Guidelines for DOT
Human Resources
PROCESS
Training of HCWs
Distribution of drugs
Supervision
OUTPUT
HCWs trained to provide DOT
Drugs available at facilities
Patients receiving DOT
Treatment outcomes reported
OUTCOME
Improved cure and treatment completion rates
Decreased failure and default rates
IMPACT
Reduced morbidity/ mortality due to TB
Prevention of MDR-TB
Logic Framework example:
Directly Observed Therapy
Notes: This is an example we have already seen in the presentation on M&E terms.
Idea is to expand on it and create a M&E logical framework that could be used to guide planning, monitoring, and evaluation of the introduction of directly observed therapy as the standard of care for smear positive TB cases.

## Slide 7: Logic Framework
Input  Process Output  Outcome  Impact
Program Level (cohort) Population level
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8: Conclusions
M&E Frameworks allow a program manager to:
Decide which program components to monitor
Plan M&E activities in a strategic and systematic way
Choose the appropriate methodology for M&E activities
Select indicators to monitor and evaluate different program components
Notes: <number>
<footer>
<header>
<date/time>
Conclusions about M&E frameworks Frameworks allow Program Manager to decide on what elements to monitor -- Plan strategically for M&E activities -- Choose appropriate methodology for M&E -- Select indicators to monitor and evaluation program implementation