## Slide 1: An Introduction to Monitoring and Evaluation for National TB Programs
Notes: The objectives of this presentation are to introduce basic concepts of monitoring and evaluation to NTP managers. By the end of the presentation, participants should understand the differences between monitoring and evaluation and how M&E will contribute to their programs. It is important to acknowledge up front that NTP managers are often already engaged in some type of M&E, and that MEASURE’s contribution to this field is the integration of systematic M&E activities into existing reporting and analysis.

## Slide 2: Overview
What is monitoring and evaluation?
How can you use monitoring and evaluation for program management?
Practical applications of monitoring and evaluation

## Slide 3: Definitions
  Monitoring is the routine reporting of data on program implementation and performance
  Evaluation is the periodic assessment of program impact at the population level and value

## Slide 4: Monitoring
Has the program been implemented according to the plan?
Are there any changes in program resources or service utilization?
Are there any weaknesses in the implementation of the program?
Where are the opportunities to improve program performance?
Notes: Monitoring activities focus on the details of your program operation. The data that we need to conduct monitoring are often routinely reported because the information needed to monitor program operation is needed on a monthly, quarterly or yearly basis.
Monitoring can help answer the following questions that program managers have: (Refer to slide)
Details:
Monitoring is the set of activities and data collection that allows an accurate understanding how the program is being implemented and whether or not the program is implemented according to the workplan. Monitoring activities can be used to detect changes in program implementation over time, for example, changes in service utilization that can be detected through routinely reported service delivery statistics. Monitoring may also be used to identify program strengths and weaknesses, such as gaps in program implementation or areas where the program is lagging behind expectations. With these data and routine reporting, program managers may also identify opportunities to improve program performance.

## Slide 5: Evaluation
Are there any changes in behavior or health outcomes in the target population?
To what extent are observed changes in the target population related to program efforts?
Notes: Evaluation activities focus on the impact of your program at the population level. True program evaluation involves the measurement of behaviors and/or health outcomes in your target population. Evaluation also implies that you are able to attribute changes in these outcomes to your program activities or interventions. Evaluation research requires a methodology or study design that allows program managers to measure the contribution of their efforts to changes in outcomes while considering the effects of other influences on those outcomes.
For example, if an NTP manager wants to address delayed diagnosis of TB through improved training of front-line health workers, he or she would have to document a decrease in the average number of days between when TB suspects are identified and when they begin treatment. However, there may be other activities or influences on the diagnostic process that are not related to the improved training. So if the manager wants to know the contribution of the training activity, he or she will have to design a research project that allows him to control for these factors. This usually involves a controlled trial, which is costly and logistically difficult to implement. For this reason, we tend to focus more on monitoring and less on evaluation.

## Slide 6: Monitoring vs. Evaluation
Level of measurement:
Monitoring Data come from routinely reported data
Example: Monthly service statistics
Evaluation Data are measured at the population level
Example: Prevalence of MDR-TB in Country X
Notes: Monitoring data come from your program, “program-based” data. The data are often reported from individual facilities, networks of facilities, district and regional offices, etc. For example, managers often receive routine reports on the number of sputum smears collected and examined for diagnostic and smear conversion tests. They may use this to determine the average number of smears performed per suspect for diagnostic purposes or the average number performed for conversion tests.
Evaluation data, on the other hand, are not routinely reported and usually require a special study or survey. With evaluation, we are measuring outcomes at the level of the target population. As we get further into the workshop, we’ll discuss the differences between monitoring and evaluation in greater detail. This workshop and the Compendium we are going to introduce focus on monitoring, because this what program managers are engaged in every day.

## Slide 7: Why is M&E important for National TB Programs?
To follow epidemiological trends in TB
To identify strengths and weaknesses in program design and/or implementation
To address changing priorities
To convince policy makers of the need for action and financial and human resources

## Slide 8: Uses of M&E for program management (1)
Informs decisions about program operations and service delivery
Ensures effective and efficient use of resources
Determine whether or not the program is implemented according to plan
Notes: REVISE SPEAKERS’ NOTES/ADD EXAMPLES.
Speaker Notes
M&E helps you make informed decisions about your program operations. It helps you make the most effective and efficient use of resources. It helps you determine exactly where your program is right on track and where you need to consider making corrections. And M&E helps you come to objective conclusions regarding the extent to which your program’s impact can be judged a “success”.
M&E is indispensable because these tools inform planners, managers, and implementers whether or to what extent the program or project is operating effectively and according to expectations. By keeping track of specific areas of program performance, operational problems can be identified while they can still be corrected and thus ongoing performance can be improved. Meanwhile, managers can also keep track of the extent to which activities are having their desired effects. Results demonstrated through good monitoring and evaluation techniques enable decision makers also to correct strategies or even overcome unanticipated difficulties.
In other words, M&E improves the program’s ultimate impact through better information and increased understanding even while activities are in progress. And as results are shared, the ongoing projects of others, and the future design of comparable activities and their implementation, likewise can all be improved.
Additional Background
An important point here is that the significance and value of M&E is realized only through use of the M&E data. It is not important in and of itself to collect numbers, even the best numbers, nor is it abstractly important to construct the perfect indicators. If data is not reviewed and interpreted and then fed back into decision-making, M&E’s ultimate purpose -- program improvement -- cannot be met. To be good M&E, it must be M&E that is actively used in problem-solving within the ongoing program, and in further steps of decision-making.

## Slide 9: Uses of M&E for program management (2)
Meets reporting requirements by different agencies and sectors of government
Evaluates the extent to which the program/project is having or has had the desired impact
Notes: FILL IN WITH EXAMPLES/SPEAKERS’ NOTES

## Slide 10: Practical applications (1)

## Slide 11: Practical applications (2)
Case Case notification
Notes: THIS SLIDE IS INCORRECT – should NOT say “prevalence” unless these data come from a true prevalence survey. It is probably really case notification. Have attempted to change it.
In this case, monitoring data on the TB notification and death rates show a gap – this program had hoped to see a much faster decline in notification and death rates after implementing DOTS, but high rates of HIV-co-infection result in a higher case notification and death rate.

## Slide 12: Practical applications (3)
Notes: More of a qualitative monitoring of availability of financial resources for TB control.

## Slide 13: Practical applications (4)
Notes: CONSIDER REPLACING WITH A TB example – perhaps one of A. Harrie’s studies in Malawi, or South Africa?