## Slide 1: Monitoring and Evaluation Frameworks
Kyiv, Ukraine
May 23, 2006
MEASURE
Evaluation
Notes: Brainstorm:
What is an M&E Framework?

## Slide 2: M&E Frameworks
Models, pictures or maps
Visualize the factors that drive an intervention
Maps that illustrate how a program should work
Identify relationships between factors that influence program operation and the successful achievement of objectives
Notes: Frameworks are borrowed from the social sciences. Helpful tool for planning programs, specific interventions, research, and M&E.
Comprehensive view of the factors that drive an intervention – the epidemiology of TB, local resources, donor efforts.
Helps us see what is contributing to challenges and successes.
Relationships can be synergistic or sometimes represent obstacles to our success.
***One example is health sector reform – can visualize how these changes will affect program with a framework and plan for anticipated challenges.

## Slide 3: Why do we use M&E frameworks?
Communication and planning tool
As a ‘map’ for program goals
Links between resources and activities
Guide selection of indicators
Notes: Purposes:
Clarify assumptions, goals, and interrelationships among factors relevant to the project or program
Define levels of performance and desired results in terms of planned activities and realistic, objective impacts
Monitoring and evaluation frameworks incorporate:
Program managers’ assumptions and objectives, in a given context
Schematic design displaying the directional linkages between key program elements and/or planned results, and other relevant factors
M&E takes place at multiple stages of a program. It is important to identify at the outset how we will gather information at each level of evaluation.
Framework drives selection of indicators and reporting process.

## Slide 4: M&E LOGICAL FRAMEWORKS
Illustrate the relationships between program Inputs, Processes, Outputs, and Outcomes.
Links the program to desired Impact.
Notes: <number>
<footer>
<header>
<date/time>
Key relationship:
Inputs are necessary to create processes, which drive the production of outputs and outcomes.
Reiterates the point on the previous slide.

## Slide 5
INPUT
Resources
Clinical and managerial Staff
Drugs
Laboratories
PROCESS
Management
Communication
Advocacy
Human resources development
Surveillance system
OUTPUT
Diagnostic services
Treatment services
Knowledge
Reduced Stigma
OUTCOME
Case detection
Case treatment
Case holding
IMPACT
TB infection
TB morbidity
TB mortality
CONTEXT
Political commitment Health system Socio-economic conditions Epi-context
Availability HIV prevalence
Access Malnutrition
Utilization Alcoholism
M&E logical framework for TB programme
Notes: Here is a generic example of an M&E framework for a national TB program. This framework shows the linear relationships between inputs, processes, outputs, outcomes, and impact. It also provides a visual interpretation of the broad context for the NTP, which includes: Political commitment
Health system variables
Socio-economic conditions
Epidemiological context of TB

## Slide 6
INPUT
Drugs
Guidelines for DOT
Human Resources
PROCESS
Training of HCWs
Distribution of drugs
Supervision
OUTPUT
HCWs trained to provide DOT
Drugs available at facilities
Patients receiving DOT
Treatment outcomes reported
OUTCOME
Cure and treatment completion rates
Decreased failure and default rates
IMPACT
Morbidity/ mortality due to TB
Prevention of MDR TB
Logic Framework example:
Directly Observed Therapy
Notes: Idea is to expand on it and create a M&E logical framework that could be used to guide planning, monitoring and evaluating the introduction of directly observed therapy as the standard of care for smear positive TB cases.

## Slide 7: Logic Framework
Input  Process Output  Outcome  Impact
Program Level Population level
Notes: <number>
<footer>
<header>
<date/time>
Another way to understand frameworks – think about the level of measurement.

## Slide 8: Conclusion
Which program components should be monitored?
Strategic and systematic planning of M&E
Appropriate methodology for M&E activities
Indicator selection

## Slide 9: Logic Framework Group Work
1. Read through the case study with your assigned group
2. Identify the goal, objectives and activities for addressing this problem and list them on form 1. Then use the logic model on form 1 to identify key inputs, processes, outputs and outcomes.
3. Each group will report back to the larger group on the draft framework/activity.